## Concept Overview
Organizing For Power Training Series Overview
As Common Cause launches Democracy Reawakening, a national organizing campaign aiming to build a vision of a multiracial and inclusive democracy by connecting everyday people into a movement community where we will strengthen our collective power to drive social and political change, we must create intentional spaces to share collective wisdom and to learn from one another. To support this organizing campaign and everyone involved, the Organizing department will launch an Organizing for Power training series. (OFP) The OFP series will serve as a recurring hybrid space where Common Cause members, volunteers, supporters, staff, and anyone looking to make Common Cause their political home can learn, reflect, and grow as activists. Participants will be trained on the skills and strategies we will need as an organization and movement to develop and leverage our grassroots power. The series will be split into two tracks to support the skill and leadership development of each participant type. The tracks below are intended as a starting point for addressing Common Cause's current training needs. Still, they will be regularly reevaluated and shifted to pivot and address newly identified gaps and needs. We understand now more than ever that to fight for the democracy we all deserve successfully, we must transform frustration into action, reimagine government, and constantly center a People-Powered future where we all have what we need to be safe, heard, and to thrive.

## Trainings Overview
Organizing For Power Training Series
WORD version of descriptions VS objectives for edits
NOTE: the order of these trainings are subject to change
Track A
| Title | Tentative Date | Description | Objective | National/State CTAs | Format | Status | Action Builder Tag | Additional Action Builder Tags
Training 1A | Organzing For Power | 2026-02-25 | This training will focus on reviewing fundamental organizing principles for building a people-powered movement and learning more how to get involved with Common Cause. | By the end of the training, participants will have a basic understanding of organizing principles and their ability to actively lead and/or volunteer in Common Cause’s campaigns and pillars. Participants will walk away with an understanding of how they can participate and engage throughout the training series. |  | Virtual 90 mins | Draft | Organizing Basics | New Member
Training 2A | Our Stories, Our Power: Storytelling for Organizing | 2026-03-25 | This training will focus on how storytelling will serve as a powerful tool for the pro-democracy movement to build connections, shift narratives, and mobilize our friends and families into collective action. Through interactive exercises and real-world examples, we will answer the question of “why”-why we care, why the work we do matters, and why we are fighting for the democracy we all deserve. | At the end of the training, participants will learn how personal and community stories can inspire action, strengthen relationships, and turn shared experiences into a catalyst for change at scale. Participants will begin drafting and practicing their “story of self” and explore using Common Cause’s new storytelling platform. |  | Virtual 75 mins |  | Storytelling
Training 3A | Changing Narratives by Centering People: The Power of Relational Organizing |  | This training will focus on the power of relational organizing and how we can build a bigger “we” to win. | By the end of the training, participants will learn how personal connections, shared values, and authentic conversations can drive deeper engagement, build lasting commitment, and strengthen our collective action. They will recognize themselves as trusted messengers in their networks. Participants will leave the training having identified 10 individuals they will commit to bringing into the pro-democracy movement. |  | Virtual 75 mins |  | Relational Organizing
Training 4A | Where Movements Begin: The Power of 1-on-1s | 2026-05-27 | This training explores the foundational role of 1-on-1 conversations in building strong people-powered movements. Through interactive discussion and hands-on practice, we will break down the purpose and the structure of an effective 1-on-1. | At the end of the training, participants will understand the purpose and structure of an effective 1-on-1, focusing on active listening, trust-building, and identifying self-interest and motivation. Participants will understand why movements begin with relationships and gain practical tools and skills to prepare for 1-on-1s. |  | Virtual 75 mins |  | Organizing Basics
Training 5A | We Keep Us Safe: Protest Safety & Bystander Intervention | 2026-06-24 | This training will prepare us to show up for public demonstrations and mobilizations with the knowledge to minimize risks and threats while keeping ourselves and each other safe. Through discussion and real-life scenarios, we will build our confidence and understanding in making thoughtful, value-driven decisions in fast-moving public settings. | At the end of the training, participants will understand basic precautions they can take to keep themselves safe, and the importance of community safety is a collective responsibility. Participants will learn key protest safety practices, including situational awareness, de-escalation strategies, understanding roles within a crowd, and responding to common risks during public mobilizations. Specifically, participants will understand the components of bystander intervention-how to recognize harm, assess when and how to intervene safely, and support others experiencing harassment, targeting, or distress. |  | Virtual 75 mins |  | Rapid Response Basics
Training 6A |  | 2026-07-29
Training 7A |  | 2026-08-26
Track B
| Title | Tentative Date | Description | Objective | National/State CTAs | Format | Status
Training 1B | X | TBD | X | X |  | TBD
Training 2B | Building Statewide Campaigns From the Ground Up | TBD | This training equips organizers with the skills and strategies to build effective, community-driven campaigns that focus on short- to medium-term victories through targeted advocacy and policy change, creating opportunities to build long-term power through leadership development and community relationships. | At the end of the training, organizers will leave with practical tools and guidance to design campaigns that reflect the needs of communities, grow and leverage grassroots power, and drive policy change across their state, turning local issues and leadership into statewide victories. Through case studies and hands-on planning, this training will cover key steps and build campaigns from the ground up, from conducting community listening sessions, mapping power and influence, setting achievable goals, and designing tactics that scale local engagement into state-level action, and so much more. |  | TBD
Training 3B | From Awareness to Action: Designing A Multidimensional Supporter Engagement Strategy | TBD | This training equips organizers with guidance, tools, and strategies to develop multidimensional supporter journeys that will move supporters from initial awareness to meaningful action within Common Cause statewide campaigns. Through interactive exercises, real-world examples, and practical planning sessions, participants will explore how to identify different levels of supporter involvement, create targeted engagement opportunities, and develop clear “next steps” that move people through a designed journey. | At the end of the training, organizers will have a deeper understanding of how to design entry points and pathways to deepen participation, build leadership, and grow/sustain our grassroots power. Organizers will leave with guidance and tools to map their supporter base, design engagement journeys at scale, and identify either national or statewide opportunities to activate their network of committed supporters to advance priority campaigns. |  | TBD
Training 4B | Building Teams That Last: Volunteer Engagement & Retention Strategies | TBD | This training equips organizers with guidance and strategies to recruit, engage, and retain volunteers and leaders to advance short- and long-term campaigns. Through discussion and Common Cause tools, we will explore key components of effective volunteer management, including identifying the right roles, creating meaningful engagement opportunities, fostering a culture of appreciation, and providing pathways for growth and leadership. | At the end of the training, organizers will learn how to build volunteer programs that not only attract new supporters and reengage existing supporters but also cultivate a culture that focuses on long-term relationships, leadership, and accountability within their teams. |  | TBD
Training 5B | TBA-Statewide Storytelling Campaigns | TBD
Training 6B | TBA-Planning & Executing Rapid Response Mobilizations | TBD
Training 7B | TBA-Strategy Evaluation Best Practices | TBD
Training 8B | From Community Power to Policy Wins: Building an Effective Legislative Strategy | TBD | This training will focus on using community organizing principles that center and empower impacted people while developing local leadership to craft our legislative strategy for upcoming legislative sessions. | At the end of the training, organizers will leave with a stronger understanding of how to center community leadership in legislative strategy, connect organizing efforts to policy outcomes, and build campaigns that move from collective action to concrete policy wins. Through interactive discussion and the use of Common Cause tools, organizers will explore key components of an effective organizing-based policy strategy, including power mapping, setting “wins” that move the needle, identifying targets, and aligning tactics with long-term movement goals.
Note on B7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: I would recommend putting this as the second training. Focuses on empowering the individual, making sure they can tell their own story, which will then make them more successful in relational organizing.
Note on E7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: For this to be most effective imo, it will be essential that we have a storytelling platform approved and set up by this training.
Note on E8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: See comment on moving storytelling up - focus on the individual empowerment first, then pull additional people in.
Note on B9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Would recommend this training also comes before the relational organizing training, so people are prepared to have those one on one conversations for the 10 people they've identified in their network.
Note on B10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Love this, Comms has been trying to work on some safety resources to share on social media because it performs really well there. Would love to partner on how we can best package this information into assets for the public.

## Execution Timeline & Links
Organizing For Power Execution Timeline
Recruitment Language | View Here
Phase 1
Task | Department/Team | Deadline | Status | Notes
Draft Concept Paper-OFP | Organizing | 2026-11-24 | Complete
Staff Feedback on Concept Paper | Invited Staff | 2026-12-19 | Complete
Phase 2
Draft finalized Trainings overview with descriptions and objectives | Organizing | 2026-01-05 | Complete
Submit PEI Scheduling Tracker for Training 1 | Organizing | 2026-01-07 | Complete
Feedback on Trainings Overview | Invited Staff |  | Ongoing
Finalize targeted digital support list for recruitment | Digital/Organizing | 2026-01-09 | Complete
Finalize Action Builder "tags" to id each training type | Organizing/Rob |  | Complete
Draft Recruitment Language for Review | Organizing | 2026-01-05 | Complete
Comms analysis of other 'People Powered Trainings' by similar legacy organizations | Comms | 2026-01-20 | Complete | Comparative Analysis
Comms review/edit recruitment language | Comms | 2026-01-30 | Done | Recruitment Language
Determine Security Precautions | IT | 2026-02-06 | Done
Create Mobilize/Zoom Meeting | Organizing | 2026-02-09 | Done | Recruitment Link
First draft of branding assets (graphics, PowerPoints, video) for training series | Comms | X | Not Moving forward | We will be using the standard Common Cause PowerPoint templates
Finalize branding asset (graphics, PowerPoints) | Comms | 2026-02-18 | Complete
Begin promotion on social media platforms | Comms | X | Not Moving forward | We will not be public recruiting. We will begin recruiting from our base of digital supporters via email.
A/B testing for recruitment language | Digital/Comms
Send Targeted Recruitment Email | Digital | 2026-02-21 | Complete
OFP website page | Digital/Comms | TBD | Ongoing
Feedback on Training 1 Outline/Slide deck | Invited Staff | 2026-02-03 | Complete
Create CTA Coordination Document | Campaigns-Izzy |  | Complete
Reoccurring
Outstanding Question Discussion | All Departments |  | Ongoing
Draft OFP 2 Recruitment Email
Send OFP 2 Recruitment Email

## Training 1 ¦ POWER
1A: Understanding Power & Community Organizing
Date | Wednesday, February 25th | Time | 6:00-7:30 PM EST |  | Format: | Zoom-Meeting Format (90 mins)
Facilitators/Staff support: | Rommel, Luana, Lamair, Tobi | Facilitator's Guide | View Here
Slide Deck | View Here | Chat Notes |  |  | Registration Link | Register Here
Description: | This training will focus on reviewing fundamental organizing principles of POWER and the need for COMMUNITY ORGANIZING, and learning more how to get involved with Common Cause. |  | Objective: | By the end of the training, participants will have a basic understanding of organizing principles like POWER and COMMUNITY ORGANIZING, and their ability to actively lead and/or volunteer in Common Cause’s campaigns and pillars. Participants will walk away with an understanding of how they can participate and engage throughout the training series.
Training Outline |  |  |  |  | Training 1 Specific Task Check List | Assignment | Status
View Working Draft Here |  |  |  |  | Create Zoom Link | Organizing | done
Time | Agenda Item | Staff | Slides | Notes | Create Mobilize Link | Organizing | done
|  |  |  | Sharing Screen -Tobi Turn on Recording-Luana Monitor Chat/Mute Attendees if needed-Tobi Staff Share Music: Start of Training: "Hell You TalmBout" - Janelle Monae f. Wondland Records. https://www.youtube.com/watch?v=fumaCsQ9wKw&list=RDfumaCsQ9wKw&start_radio=1 End Music: "Alright": Kendrick Lamarr (start at 0:18sec. mark) https://www.youtube.com/watch?v=6QbLcwVAsl0&list=RD6QbLcwVAsl0&start_radio=1 | Notify Digital & Comms for recruitment email | Organizing -Digital | done
6:00-6:10 PM EST (10 mins) | Introductions, Housekeeping, Community Norms, Grounding | Luana | Slides 1-7 |  | Review recruitment email for training | Organizing | done
6:10-6:18 PM EST (8 mins) | breakout room-getting to know each other | Luana | Slide 8 |  | Submit training to PEI (calendar) | Luana | done
6:18-6:28 PM EST (10 mins) | Making Meaning | Rommel | Slides 9-13 |  | Create Slide deck & add standard content slides | Organizing | done
| Poll: Pre-assessment | Rommel | slide 14 |  | Invite state Organizers | Organizers-Everyone reaches out to their assigned states | done
6:28-7:08 PM EST (40 mins) | Power & Community Organizing Overview | Lamair | Slides 15-28 |  | Post-Training Survey | https://forms.gle/JWoNNRN87TN2q5r18
7:08-7:25 PM EST (17 mins) | Breakout Rooms Instructions & Discussions | Luana | Slides 29-30 |  | Follow-Up Email | Luana | pending
Breakout Room Debrief
7:25-7:30 PM EST (5 mins) | Calls To Action & Next Steps | Luana | Slides 31-36 | Tobi-share state CTA map link https://www.commoncause.org/grassroots-actions/ | https://www.commoncause.org/actions/tell-congress-reject-the-anti-voter-save-act/
| Upcoming Reminders |  |  | https://www.mobilize.us/commoncause/event/758610/

## Training 2 ¦ Storytelling
2A: Storytelling
Date | Wednesday, March 25th 2026 | Time | 7:00-8:15 pm EST (Prep: 6:45pm) |  | Format: meeting with breakout rooms | Zoom-Meeting Format (90 mins)
Facilitators/Staff support: | Luana, Lamair, Tobi, Carlos | Facilitator's Guide | View Here | Story of Self Planning Guide
Slide Deck | View Here | Chat Notes |  | Top roles: Tobi share screen and music on zoom | Registration Link | Register Here
Description: |  |  | Objective:
Training Outline
View Working Draft Here
Time | Agenda Item | Staff | Slides | Notes
6:57-7 | Welcome chat sharing | Carlos |  | Chat questions - In the chat tell us: Name, where are you joining us from, is this your first time joining common cause, did you attend the last training
7-7:05 | Welcome, Community Agreements, CC Priorities | Carlos | Slides 1-5 | Chat questions - In the chat tell us: Name, where are you joining us from, is this your first time joining common cause, did you attend the last training
7:05-7:08 | Organizing For Power Session #1 Recap | Carlos | Slides 6-7
7:08-7:10 | Community Baseline | Carlos | Slides 8 | Chat questions - In the chat tell us: (1) A story that made you get involved or care about an issue (2) How have you used storytelling to advocate for change? (choose 1-2 people to share based on their chat message)
7:10-7:12 | Storytelling is the Backbone of Organizing | Lamair | Slides 9
7:12-7:17 | What is Storytelling | Lamair | Slides 10
7:17-7:25 | Storytelling in Action | Lamair | Slides 11 | Share a video of a story and how it was incorporated with a campaign
7:25-7:27 | Power of Story | Lamair | Slides 12
7:27-7:30 | How to Tell Your Story (2x) | Lamair | Slides 13-14
7:30-7:35 | Q&A (in chat) | Lamair | Slides 15 | People write questions in the chat
7:35-7:37 | Call To Action; State campaigns; No Kings rally | Tobi | Slides 16-17
7:37-7:42 | Overview of breakout rooms | Luana | Slides 18-19
7:42-8:00 | Breakout Room Session: Storytelling Deep Dive (101 vs. 201) | Lamair, Luana, Carlos, Tobi |  | 101 participants will be automatically assigned to a breakout room with a staff member to walk through the Story of Self worksheet. 201 participants can elect to stay in the main room to participate in the Soapboxx activity
8:00-8:10 | Breakout Room Debrief | Carlos
8:10-8:13 | Next Steps | Tobi | Slides 20-22
8:13-8:15 | Close | Carlos | Slides 23
Training 2 Task List | Due Date | Staff Assignment | Status | Notes
Draft Recruitment Email | rolling basis | Jack | Done
finalize polls and create on Zoom | 2026-03-20 |  | Done
Send Email Reminder to Digital | 2026-03-17 | Luana | Done
Send Recruitment Email | 2026-03-18 | Digital- Jack | Done
Send Day-off Reminder Email | 2026-03-25 | Digital- Jack | Pending
Draft follow-up email | rolling basis
Send follow-up email | 2026-03-26 | Organizing - Carlos | pending
Technical Assignments | Staff Assignment | Notes
Start the Meeting | Carlos
Start recording | Carlos
Pause recording and restart the recording after breakout rooms | Tobi
Share slides | Tobi
Start music at the start of the training | Tobi